## Sheet1
ID | Area Path | Title | Defect Type | Symptom
29770 | Evolution\ERP | Source is "None" on the customer and CRM has marketing company - causing billing and biling adjustments and payments to fail | Break Fix | The Source field is populating as 'None' for some of the SAP customers. This is causing the billing and Bill adjustments to error in the staging tables. Socratis identified approximately 12,000 that need to be fixed in CRM and then the customer can update in AX to correct; Socratis to attach a list
29982 | Evolution\ERP | Billing is not processing in the billing staging table due to item id being none (long term fix) | Break Fix | Bilings are not processing in the billing staging table. It appears the item id is not populating correctly. This needs to be addressed ASAP because cancellations are being processed and the information is not correct. This field drives how the product is identified. There needs to be a query to identify all customers that have a item customer group of none - and determine which of those should be SAP, Nashville, Orlando, Vertex, or EPCOR. Only NWB should be none. See attached for example. There are approximately 10,000 billings in staging due to this .
30018 | Evolution\ERP | WB Billing adjustments are not processing in the bill adjust staging table | Break Fix | There is a large volume of billing adjustments in staging in error. There were a Large amount of adjustments processed for UPI. These are not processing due to some of the these enrolments are expired or cancelled over 90 days prior. The logic of the table needs to be look at to determine why all the adjustments are getting stuck and how to proceed.
30044 | Evolution\ERP | go live - Payment files can be processed multiple times in AX - may also apply to other files | Enhancement | Need to develop process so that payment files are not consumed multiple times. Same with billing and billing adjustment.
30061 | Evolution\ERP | orlando billing, adjustment and payment files | Enhancement | Orlando files as existing may not produce adequate results and will need to be manually intervened.
30065 | Evolution\ERP | Billing is failing in staging due to error"there is no active enrollment for the customer and product (Long-Term) | Break Fix | Orlando billing is in error in the staging table. Orlando billings are failing in the staging table. the error is there is no active enrollment. There are renewals , but the billings are not seeing the renewal and are not billing. Some of the errors are saying the enrollment is fully billed. See attached list of billings in the staging table. This is happening in AWRL and billings are getting stuck in error in staging. These should be billing and not error in staging. The renewal is not billing because the effective date is the same as the earning date. The effective date should be when the enrollment renewed and sent to AX, this should not be the same as the earning date, something changed - the effective date used to be the date the customer renewed so this was not the same as the earning date. Not sure what changed this in CRM.
30073 | Evolution\ERP | Change request - AR auto settlement of Credits | Enhancement | AX has an out of the box settlement to apply credits to open AR. This does not work for HOS because if a customer is being refunded, the credit was settling to open AR for a different product. There needs to be a process that runs daily to settle credits to open AR. This is caused by Billing Adj that are credits do not settle against debit adjustments, Payments that leave a credit on the customers account and then the billing comes in - does not settle. and credits that process for nonwaterbill transactions. do not auto settle. The process should be run so that the credits settle to the same product first.
30127 | Evolution\ERP | CRM sends enrollment and cancellation to AX - AX does not build revenue table and cancels enrollment |  | CRM is processing an enrollment and cancelling the same day. The enrollment and cancellation come to AX but the revenue table is not updating. See attached for examples. These adjustments/refunds are stuck in the &quot;Request refund staging table: - not sure how to get these processed to refund the customer. and stop this from happening in the future.
30163 | Evolution\ERP | NWB CC enrollment cancelled - billing adjustment is not recorded |  | NWB Enrollments cancelled in CRM and calculation is correctly done - cancellation updated in AX, the open AR reversed, but the billing adjustment is not recorded in AX. See attached. need to see if this is a scribe failure or why this adjustment did not come to AX The adjustment is not in the request refund staging table
30187 | Evolution\ERP | Service Fee Refunds are not processing through the staging as refunds | Break Fix | Service Fee refunds are not processing through AX as a refund. Claims sent through 2 refunds for Service Fee and these came into staging, but processed in AX as billings. see attached for examples. These should process as credits in AX and go through the AR reimbursement process.
30188 | Evolution\ERP | Service Invoice Billing does not always come to AX to Bill |  | Claims will process a Service Fee. This should come to AX to the Claim Service Fee staging table and process a Service fee for $50.00. These Service fee billings sometime come over to Ax and other times do not. We have found that AX receives a payment , but the billing is not processed and the the transaction is not in the staging table. see attached fro example.
30193 | Evolution\ERP | Billing Staging Table - Update dates to currrent dates for attached enrollments so the billling will processs |  | Attached is a list of billing transactions stuck in staging due to the billing date is a closed period. Update these transactions to a current date so the bills can process., Also - Nashville and Epcor have been reconciled through the end of may - any billing transactions for these third parties should be deleted from the billing staging through the end of May 2017.
30195 | Evolution\ERP | Billing Staging Table - not processing transactions | Break Fix | The Billing staging table has valid transactions error in staging with the error message = There is no active enrollment for the Customer CUS-0000000000243717 and the product EIHP-WTB, (this is an example of the error message - the customer number and product will be different for each enrollment) There is an active enrollment and customer for the billing transactions and has billed in previous months. See attached for example. more examples are in the billing staging table.
28639 | Evolution\CRM | Billing team needs work flow set up to be able to clear out queue items in bulk. | Break Fix | Billing team needs work flow set up to be able to clear out queue items in bulk. When something happens with the response file coming in from the 3rd parties, EX: the response file is blank, all items that are in the staging table fall into the HOS5 exceptions queue. This could be hundreds or even thousands. The billing team has to go into each item and open up the enrollment, look at the audit history to see what the previous enrollment status and reason was, change the enrollment status and reason, and then close out the queue item detail. I am attaching a copy of the SAP Cancellation queue from today to show the impact of this. I spoke with Darin and he said a work flow could be set up for billing to be able to bulk edit the enrollment status and reason back to the previous state and also close out the queue item detail.
29125 | Evolution\CRM | Need report to validate that claims are created as PO in AX | Break Fix | Due to questions from controls about integration failures on customers and enrollments (28306); and the high level of exceptions when attempting to pay contractor invoices - the need for a report to determine what claims failed to create POs in needed.
29127 | Evolution\CRM | Cancellations finalized in CRM are not cancelling enrollments in AX | Break Fix | Enrollments cancelled in CRM (mostly shut offs) are not cancelling the enrollments in AX. Examples are the following ENR1002763329 ENR1001163540 ENR1000354990 ENR1003043129 ENR1000913247 These examples are Nashville - there are other enrollments that did not cancel in AX.- need to understand if there are more besides Nashville and also how to correct these so the enrollments cancel in AX. CRM has a defect 28994 - this is Nashville and Orlando shut off files -not sure if this is related.
29168 | Evolution\CRM | Aging buckets on the customer form in CRM only allow positive values from AX - should also allow negatives |  | Aging buckets on the customer form in CRM only allow positive values from AX - should also allow negatives. When a negative amount comes from AX, CRM is not updating with the information. This is causing our delinquency totals to be incorrect. We currently have 9000 delinquencies in our queue.
29198 | Evolution\CRM | Adjustments are being created without Adjustment Reasons | Break Fix | Adjustments are being created without Adjustment Reasons. I have created an Advanced Find for adjustments created without an Adjustment Reason (see attached). There are 126 adjustment created during the cancellation that do not have an adjustment reason. These adjustments are not being picked up on the outbound files. Therefore, the customers accounts are not getting the adjustments. I have attached a copy of an adjustment record to show the field that is not being populated. AES 11/8/2016: We believe that this is happening only to products (In home plus) that do not have an adjustment reason. Customers are not receiving the proper credit to their water account.
29482 | Evolution\CRM | Paid Legacy Claims not populated in CRM Paid Amount Field | Break Fix | There are over 17,000 Legacy claims which have been paid but do not have the Paid Amount field populated in CRM. I believe this is causing CRM to open a PO in AX since the system believes the claim still needs payment. I've attached the list of paid claims and an advanced find screen shot of what field should be populated with this data in CRM. Please let me know how I can be of assistance. We continue to keep about $20M open on the Open PO report for claims that are paid due to this defect. Please see screenshot and attachment. <img height=95 style="width:1104px;height:182px;" src="http://ame001-tfssc01.ame001.americanwaterservices.com:8080/tfs/Evolution/WorkItemTracking/v1.0/AttachFileHandler.ashx?FileNameGuid=4e69d227-6ab0-422a-907f-1eff4bf9df4c&amp;FileName=temp1484317876293.png">
29504 | Evolution\CRM | Delinquency cancellation not updating the WO amount in total on CRM - adjustment plus tax | Break Fix | Delinquency cancellations are processed in CRM - AX is calculating the WO amount and tax. The correct amounts are being sent form AX to CRM. The correct amount in total is not populating on the enrollment cancellation screen. The correct amounts are on the Write off screen shot broken out by billing adju and tax amount see screen shot for details.
29548 | Evolution\CRM | Cancellation date can not exceed the Enrollment expiration date | Enhancement | The cancellation date can not exceed the enrollment expiration date or end date. If CRM puts in a date that is past the end or expiration date, the system will calculate addiational revenue. Each enrollment can only earn revenue through its expiration or end date. see attached.
29567 | Evolution\CRM | Customers and Enrollments failing to integrate to AX from CRM | Break Fix | Customers and Enrollments fail to integrate to AX. Weekly report ran and process is to run the workflows in CRM to send back over; but the trend continues. Latest few reports attached
29588 | Evolution\CRM | Paid Amount field not updated - Failed Integration from AX to CRM | Break Fix | Defect 29164 has been resolved in ERP - now a CRM Issue for not accepting all paid amounts. Please review There are thousands of claims that have been paid and the paid amount field did not update in CRM. This is throwing off all financial reporting and BI. Please see attached list for the historical data to catch up. These claims have been identified from finance team; I'm also attaching what I have located in the system to be closed with an invoiced amount and no paid amount. 11/14-Sashi: We have analyze the attached vendor invoices which has been in question, why those vendor payment information did not send to CRM, we have analyzed and attached the document (DF_29164) with our findings. 1. Most of the POs are not invoiced in AX. so no payment information available to send it to CRM. 2. On 19th October most of the invoice processed with the transaction date as 18Th (Back dated). As the current batch/business process picks the vendor payments only for the transaction date which are set to be current date i.e. the payment processed for the said day at the day end and send it to CRM. As 19th Oct we have process with back date 18th Oct those payment information did not pass over to CRM.
29606 | Evolution\CRM | Paid by PCard state should update paid amount field, not to come from AX | Enhancement | When a claim is Closed status and &quot;paid by pcard&quot; state - then AX will not get the information to send over to the paid amount field. This should come from CRM to update paid amount. Need to discuss specific examples, but the primary one would be if it is closed as paid by pcard, use the invoiced amount as the paid amount. In the event there was already a paid amount from AX and now we close by PCard for a second, the amount should add to the existing, not overwrite. THis is a change, as the paid by pcard should still go over in AX integration to void the PO; but then have a separate piece to now update paid amount.
29613 | Evolution\CRM | Invoice number changed upon opening and closing invoice record | Break Fix | Invoice number changed upon opening and closing invoice record. I am attaching the email chain with screen shots of the error. The invoice number changed from C355796 to B287669.
29684 | Evolution\CRM | SAP customers are in AX as source=none - this is causing billing to fail |  | Billings for SAP are failing in the staging table because the customers are coming into AX with the source=none. source has to equal SAP. Short term fix to process the billing is to identify SAP account numbers starting with 2100 and 2200 and update the source from none to sap Socratis and AJay are identifying. Long term need to fix CRM so that the correct information is sent to AX. ERP is fixing already existing data in 29355. Assigning this one to CRM for permanent fix. It was found that CRM is sending customer data to AX with source customer None. Records reference third party marketing - did you add a source customer that maybe AX didn't.?
29694 | Evolution\CRM | CRM is changing the service fee status | Break Fix | CRM is changing the service status after a billing representative has already updated the field and saved the record. This defect impacts our customer and our financials. Please see attachment.
29796 | Evolution\CRM | ICRM60_PaymentsETS_AWCC Failure Fetching Source Row | Break Fix | CC files coming into scribe seem to be processing but on certain days scribe calls a Fatal Error saying Failure fetching source row. All of the records on the file seem to have processed and when compared to successful files I do not notice differences in the format or data. The job seems to get through a certain # of records and just stop going through the file. Attached file was run on 3/23 at 1:56 pm EST in production. 1537 records on the file only 60 were processed
29876 | Evolution\CRM | CRM aging buckets are not updating when enrollment falls off the delinquency file | Break Fix | CRM aging buckets are not updating when enrollment falls off the delinquency file. When an enrollments falls off the delinquency file, the aging buckets are not updating to $0.00. There is no workaround for this and it causes enrollments to flip back to delinquent when the aging buckets are not updating.
29901 | Evolution\CRM | Need to automate workflows to send Customers/Enrollments to AX | Break Fix | Need to automate the workflows on the failed customers and enrollments to AX (CRM Mismatch report) that is ran weekly. Need to automate this to run 2x a week to pull the records not in AX; then update the below workflows to send the records again Integration - Customer Info Updated Integration - Enrollment Info Updated Still need the report for URC08 for IA to run on Wednesdays to show any mismatches. This report has been pulling NYC customers as of recently, need that fixed before any further update to automate the sending to AX.
30010 | Evolution\CRM | Delinquency/Non Delinquency jobs cannot handle large volumes |  | The Enrollment Delinquency and Enrollment Non Delinquency jobs that run each day can get over 200,000 records. This ends up taking 24+ hours in production (see weekend of 5/13/17 and 5/19/17 for record counts). These jobs need to be redesigned to complete much faster. This change should also be done on the ContactDelinquence and Contact Non Delinquency as well.
30070 | Evolution\CRM | Virginia delinquent accounts should go to Pre-Cancellation Notification after 45 days until 75 days delinquent | Break Fix | Virginia delinquent accounts should go to Pre-Cancellation Notification after 45 days until 75 days delinquent. Virginia is an insurance state and they are supposed to get a pre-cancellation letter at 45 days and get cancelled at 75 days. I am attaching the audit history of an enrollment where it went to Pre-Cancellation Notification on 5/28 and then to Cancelled on 5/30. This is causing us to not be able to send Virginia customers pre-cancellation letters giving the customer 30 days to pay their account in full before cancelling them.
30123 | Evolution\CRM | Create one time job clearing out AX refund date on Enrollment to resend cancellation refund to AX | Break Fix | Create a onetime job to clear out the ax refund date on the enrollments to trigger cancellation refund to resend to AX.
30124 | Evolution\CRM | Update Refund Job to Configurable Values | Break Fix | Update Refund job to use configurable values for the refund code in the adjustment integration to AX – currently all values are hardcoded.
30125 | Evolution\CRM | Add new AX Enrollment/Cancellation Sent Date fields to CRM and update refund job to send when populated | Enhancement | Update CRM to have an AX Enrollment/Cancellation Sent Date and update refund job to only send when those are populated (also update queue based jobs to populate new date fields where appropriate). This should only occur for adjustments that are tied to a cancellation refund and not one-time/ad hoc adjustments, all others should be sent as normal.